## Start Here
Free Project Delivery Health Check — Interim Week 2 Acquisition MVP / Self-Assessment Workbook v0.1
Use this interim workbook to structure your own evidence, self-rate the frozen 12 Health Check checks, and see deterministic gaps and priorities while the automated Health Check remains a future implementation target.
Step | What to do | Free workbook boundary
1 | Open Health Check and enter the basic project context in yellow cells. | This is a structured self-assessment. It does not independently interpret or verify unstructured project evidence.
2 | Rate all 12 checks using 0–4 or NE. A numeric rating counts only when you also add a supporting evidence note. | It can organize your evidence and calculate deterministic coverage/score logic only when a numeric self-rating has a supporting note.
3 | Add a short evidence note for every numeric rating; record missing information where relevant. | It does NOT independently validate evidence, detect/reconcile contradictions, validate threat claims, or provide paid-Audit professional judgment.
4 | Complete the material-gap / contradiction / escalation flags honestly from your own evidence. | Paid Audit: Project Delivery Health Audit — $199 beta.
5 | Open Results, Missing Info and Priority Actions. | Use the Audit when the decision matters enough to require an independent review of actual evidence.
6 | Use the $199 Project Delivery Health Audit when you need independent evidence challenge and professional judgment. | Audit CTA: https://techmanagersplaybook.com/project-delivery-audit/
Input legend: yellow cells = editable. Gray/blue cells = formulas or reference content; do not overwrite them.
Protection design: all intended user-entry cells are yellow and validated where categorical. Calculation/output cells are isolated on formula/output sheets and visually marked. Do not overwrite gray/blue formula cells.
Phone use: on the Health Check tab, you only need columns A–H. The calculation columns sit to the right and the readable outputs are on Results, Missing Info and Priority Actions.

## Health Check
Project Delivery Health Check — Interim Week 2 Self-Assessment Workbook | [11 empty] | Internal calculation | Value
[12 empty] | Evidence coverage | 0%
Internal observed score
[12 empty] | Trajectory assessable? | No
Project context | Your input |  | Evidence-quality flags | Your answer | Guidance | [6 empty] | Risk core assessable? | No
Project / initiative name |  |  | Material missing information present? | No | Yes only when a missing item could materially change the delivery judgment. | [6 empty] | Decision core assessable? | No
Status date |  |  | Does that missing information block a defensible current-state judgment? | No | Use Yes only when you cannot responsibly judge the current commitment/trajectory without it. | [6 empty] | Reporting core assessable? | No
Major commitment / milestone |  |  | Material contradiction present? | No | A material conflict between current project claims/facts, not a minor wording difference. | [6 empty] | Material missing? | No
Target date |  |  | Does that contradiction block a defensible current-state judgment? | No | Use Yes when the conflict prevents a defensible current-state judgment. | [6 empty] | Missing blocks judgment? | No
Current reported RAG (optional) | Red |  | Material contradiction undermines the stated current project position? | No | Use Yes when the conflict directly weakens the stated status/forecast. | [6 empty] | Material contradiction? | No
Do you have meaningful current project-delivery evidence? | Yes |  | Self-declared material commitment threat? | No | Use Yes only when your own explicit evidence supports a serious threat to a major delivery commitment; add the supporting note below. The workbook does not independently validate it. | [6 empty] | Contradiction blocks judgment? | No
[12 empty] | Self-declared material commitment threat (with note)? | No
|  |  | Self-declared material commitment threat evidence note | [8 empty] | Self-declared Red-trigger count (with notes) | 0
|  |  | Evidence / rationale (required if Yes) | [8 empty] | Confidence | Insufficient
[12 empty] | Numeric score eligible? | No
Check | Signal area | Plain-English guidance | What good looks like | Weight | Your rating | Evidence / note | Missing information / what to verify | Assessable weight | Weighted points | Priority | Default next action | Green core gate? | No
H1 | Delivery trajectory | Commitment / target clarity: Is the major delivery commitment or milestone clear, current, and time-bound? | A named major commitment/milestone, target date, and current scope/baseline are explicit. | 12.5% |  |  |  | 0% | 0% | Not rated | Confirm one major commitment, milestone and target date; clarify the current baseline. | Delivery signal | Not enough evidence
H2 | Delivery trajectory | Progress / forecast credibility: Does current progress support the stated forecast or target? | Actual progress, variance, remaining work and recovery/reforecast evidence support the forecast. | 12.5% |  |  |  | 0% | 0% | Not rated | Compare actual progress with plan; update forecast and recovery/reforecast where needed. | Score public label | Not enough evidence
R1 | Risks & issues | Risk / issue visibility: Are the material delivery risks and issues visible? | Material risks/issues are explicitly listed with impact and current status. | 7.5% |  |  |  | 0% | 0% | Not rated | List the current material delivery risks/issues and their delivery impact.
R2 | Risks & issues | Risk response / ownership: Do material risks/issues have accountable responses? | Material risks/issues have an owner, response, target date and escalation path where needed. | 7.5% |  |  |  | 0% | 0% | Not rated | Assign accountable owners, response dates and escalation paths to material risks/issues.
D1 | Decisions & dependencies | Decision / dependency visibility: Are unresolved decisions and critical dependencies visible? | Critical dependencies and unresolved decisions are explicitly identified with delivery impact. | 10% |  |  |  | 0% | 0% | Not rated | List unresolved decisions and critical dependencies that can affect delivery.
D2 | Decisions & dependencies | Decision / dependency control: Are decisions and dependencies actively controlled? | Owners, due dates, aging/impact and escalation are visible for material decisions/dependencies. | 10% |  |  |  | 0% | 0% | Not rated | Assign owners/dates and actively track decision/dependency impact and aging.
S1 | Scope & requirements | Scope / change clarity: Is the current scope clear and are material changes controlled? | Current scope/baseline is clear; material changes are explicit and incorporated into planning. | 5% |  |  |  | 0% | 0% | Not rated | Confirm current scope and ensure material changes are explicitly approved and planned.
S2 | Scope & requirements | Acceptance / stakeholder implications: Are acceptance expectations and stakeholder implications clear? | Acceptance criteria, requirement implications and stakeholder alignment are sufficiently explicit. | 5% |  |  |  | 0% | 0% | Not rated | Clarify acceptance criteria and any stakeholder/requirement implications affecting delivery.
A1 | Ownership & execution | Action ownership / follow-through: Do material delivery actions have owners and due dates? | Consequential actions have accountable owners, dates and visible follow-through. | 7.5% |  |  |  | 0% | 0% | Not rated | Assign owners and due dates to material actions; close or replan stale actions.
A2 | Ownership & execution | Execution / stakeholder alignment: Are delivery teams and key stakeholders aligned on the current path? | Key handoffs, sequence and stakeholder expectations are aligned enough to execute. | 7.5% |  |  |  | 0% | 0% | Not rated | Resolve cross-team/stakeholder alignment gaps and confirm the next handoffs.
E1 | Reporting & evidence | Status claims supported by evidence: Are status/RAG/forecast claims supported by dated delivery facts? | Reported status is traceable to current progress, milestones, risks, decisions and other delivery evidence. | 7.5% |  |  |  | 0% | 0% | Not rated | Support status/RAG claims with dated delivery facts rather than assertion alone.
E2 | Reporting & evidence | Consistency / currentness / decision utility: Is the project information current, internally consistent and useful for decisions? | Key updates are current, contradictions are reconciled or visible, and leadership can act on the information. | 7.5% |  |  |  | 0% | 0% | Not rated | Reconcile stale/conflicting updates and make material evidence gaps explicit.
Self-declared Red-trigger flags | Applies? | Evidence note (required for Yes) | Use Yes only when your own explicit evidence supports the condition
Major commitment already failed with no credible recovery/reforecast | No |  | FAILED_COMMITMENT_NO_RECOVERY
Imminent major milestone/release is blocked or demonstrably infeasible | No |  | IMMINENT_MILESTONE_BLOCKED_OR_INFEASIBLE
Material issue has near-term delivery consequence and no accountable response/recovery | No |  | MATERIAL_ISSUE_NO_ACCOUNTABLE_RESPONSE
Reported status/forecast is contradicted by stronger evidence showing commitment is not credible | No |  | REPORTED_STATUS_CONTRADICTED_BY_STRONGER_EVIDENCE
Submitted/current evidence explicitly says the key target cannot be met | No |  | TARGET_EXPLICITLY_CANNOT_BE_MET
These are self-declared escalation flags. The workbook checks that a supporting note exists; it does not independently validate the evidence, contradiction, or threat claim.

## Results
Your Project Delivery Health Check Results
Result | Value |  | How to read this
Self-Assessed Delivery Health Score | Not enough evidence |  | Green: delivery appears on track based on your own structured evidence; no material unresolved condition currently threatens a major commitment.
Evidence coverage | 0.0% |  | Amber: delivery remains feasible, but significant issues, uncertainty or control weaknesses require management attention.
Evidence confidence | Insufficient |  | Red: your self-declared evidence/serious-threat flags indicate a serious threat to a major delivery commitment requiring urgent intervention, recovery, major decision or re-baselining.
Self-Assessed Delivery Signal (RAG) | Not enough evidence |  | This is a deterministic self-assessment signal. The workbook does not independently validate evidence, contradictions or threat claims.
Paid Audit escalation | Project Delivery Health Audit — $199 beta
Signal area | Assessable weight | Weighted points | Area score
Delivery trajectory | 0% | 0%
Risks & issues | 0% | 0%
Decisions & dependencies | 0% | 0%
Scope & requirements | 0% | 0%
Ownership & execution | 0% | 0%
Reporting & evidence | 0% | 0%
Overall | 0% | 0%
Need an independent evidence-backed assessment?
The $199 Project Delivery Health Audit independently reviews actual evidence, challenges material gaps/contradictions, and returns evidence-backed findings and actions. Learn more: https://techmanagersplaybook.com/project-delivery-audit/
Limitations: this interim self-assessment workbook uses your own ratings, evidence notes and flags. It cannot independently verify completeness, validate contradictions or threat claims, challenge optimistic reporting, or substitute for the paid evidence-backed Audit.

## Missing Info
Missing Information / Evidence Gaps
Check | Check area | Your rating | What is missing / to verify | Suggested evidence to gather | Why it matters
Rule: a numeric rating without a supporting evidence note is unassessable. Missing information alone never creates a negative rating or a Red result.

## Priority Actions
Priority Action View
Check | Area | Rating | Priority | Recommended self-management action | Your evidence / note
H1 | Delivery trajectory |  | Not rated | Confirm one major commitment, milestone and target date; clarify the current baseline.
H2 | Delivery trajectory |  | Not rated | Compare actual progress with plan; update forecast and recovery/reforecast where needed.
R1 | Risks & issues |  | Not rated | List the current material delivery risks/issues and their delivery impact.
R2 | Risks & issues |  | Not rated | Assign accountable owners, response dates and escalation paths to material risks/issues.
D1 | Decisions & dependencies |  | Not rated | List unresolved decisions and critical dependencies that can affect delivery.
D2 | Decisions & dependencies |  | Not rated | Assign owners/dates and actively track decision/dependency impact and aging.
S1 | Scope & requirements |  | Not rated | Confirm current scope and ensure material changes are explicitly approved and planned.
S2 | Scope & requirements |  | Not rated | Clarify acceptance criteria and any stakeholder/requirement implications affecting delivery.
A1 | Ownership & execution |  | Not rated | Assign owners and due dates to material actions; close or replan stale actions.
A2 | Ownership & execution |  | Not rated | Resolve cross-team/stakeholder alignment gaps and confirm the next handoffs.
E1 | Reporting & evidence |  | Not rated | Support status/RAG claims with dated delivery facts rather than assertion alone.
E2 | Reporting & evidence |  | Not rated | Reconcile stale/conflicting updates and make material evidence gaps explicit.
These actions are a generic deterministic action library linked to your self-rating. They are not evidence-backed professional recommendations from the paid Audit.

## Example
Example / Demo — do not use as your assessment
Check | Example rating | Example evidence note | Example missing info | Priority | Signal area | Weight | Purpose
H1 | 4 | 30 Sep release target; scope baseline confirmed. |  | None | Delivery trajectory | 12.5% | Illustrates a healthy, well-evidenced self-assessment.
H2 | 4 | Sprint complete; UAT 80% complete with remaining work dated. |  | None | Delivery trajectory | 12.5% | Illustrates a healthy, well-evidenced self-assessment.
R1 | 3 | Vendor certification risk explicitly listed. |  | Watch | Risks & issues | 7.5% | Illustrates a healthy, well-evidenced self-assessment.
R2 | 4 | Risk has owner, date and fallback. |  | None | Risks & issues | 7.5% | Illustrates a healthy, well-evidenced self-assessment.
D1 | 4 | Legal dependency and sponsor decision are listed. |  | None | Decisions & dependencies | 10% | Illustrates a healthy, well-evidenced self-assessment.
D2 | 3 | Owners/dates exist; escalation trigger could be clearer. |  | Watch | Decisions & dependencies | 10% | Illustrates a healthy, well-evidenced self-assessment.
S1 | 4 | Scope frozen except one approved change. |  | None | Scope & requirements | 5% | Illustrates a healthy, well-evidenced self-assessment.
S2 | 4 | Acceptance criteria updated; stakeholders reconfirmed sequence. |  | None | Scope & requirements | 5% | Illustrates a healthy, well-evidenced self-assessment.
A1 | 4 | Material actions have owners and due dates. |  | None | Ownership & execution | 7.5% | Illustrates a healthy, well-evidenced self-assessment.
A2 | 4 | Product, Engineering and Operations aligned on release sequence. |  | None | Ownership & execution | 7.5% | Illustrates a healthy, well-evidenced self-assessment.
E1 | 4 | Green status supported by progress/UAT facts. |  | None | Reporting & evidence | 7.5% | Illustrates a healthy, well-evidenced self-assessment.
E2 | 4 | Update is dated and internally consistent. |  | None | Reporting & evidence | 7.5% | Illustrates a healthy, well-evidenced self-assessment.
Your live Health Check sheet is intentionally blank. Use this tab only to understand the expected level of evidence detail.

## Automated Mapping
Workbook → Future Automated Health Check Mapping
Workbook element | Workbook v0.1 role | Future automated Health Check | Frozen contract mapping | Automated later? | Paid-Audit-only boundary | Validation signal
Project context | User enters structured context | Model extracts equivalent context from project_text | Input context around project_text | Yes | Paid Audit may request/verify broader evidence pack | Completion + data quality
12 self-ratings | User supplies 0–4/NE; numeric ratings count only with evidence note | Model proposes 12 ratings; app validates | checks[] | Yes | Paid Audit remains 35-check independent review | Rating distribution
Evidence notes | User supplies own support | Model extracts evidence[] from text | evidence[] | Yes | Paid Audit independently challenges/validates evidence | Evidence-note completion
Missing-information notes | User identifies known gaps | Model proposes missing_information[] | missing_information[] | Yes | Paid Audit determines materiality through review | NE frequency / gap themes
Material missing/contradiction flags | User self-declares | Model proposes structured flags; app applies rules | missing_information[] / contradictions[] | Yes | Paid Audit independently detects/reconciles contradictions | Flag frequency
Red-trigger flags + evidence note | User self-declares serious condition + supporting note | Model proposes red_trigger_candidates[]; app validates | red_trigger_candidates[] | Yes | Paid Audit applies professional judgment to actual evidence | Escalation incidence
Material commitment threat | User self-declares material commitment threat + supporting note | Model proposes structured threat | material_commitment_threat | Yes | Paid Audit independently assesses materiality | Threat incidence
Evidence coverage formula | Deterministic Excel formula | Deterministic application formula | Section 1.5 | Same rule | None | Coverage distribution
Observed score formula | Deterministic Excel formula | Deterministic application formula | Section 1.6 | Same rule | None | Score distribution
Confidence rules | Deterministic from structured inputs | Deterministic app logic | Section 1.7 | Same rule | Paid Audit confidence derives from reviewed evidence | Confidence distribution
RAG route | Deterministic self-assessment route | Deterministic app logic after model proposal | Sections 1.9–1.10 | Same rule | Paid Audit conclusion is independent/manual | RAG distribution
Priority action library | Generic rule-based next steps | Future model may propose contextual actions | recommended_next_actions[] | Partly | Paid Audit provides evidence-backed recommendations | Most common action needs

## Reference
Rating | Meaning | Yes / No | Check ID | Signal area | Check | Plain-English question | What good looks like | Weight | Default action
4 | Strong explicit evidence of effective control | Yes | H1 | Delivery trajectory | Commitment / target clarity | Is the major delivery commitment or milestone clear, current, and time-bound? | A named major commitment/milestone, target date, and current scope/baseline are explicit. | 12.5% | Confirm one major commitment, milestone and target date; clarify the current baseline.
3 | Generally controlled; minor gaps | No | H2 | Delivery trajectory | Progress / forecast credibility | Does current progress support the stated forecast or target? | Actual progress, variance, remaining work and recovery/reforecast evidence support the forecast. | 12.5% | Compare actual progress with plan; update forecast and recovery/reforecast where needed.
2 | Mixed / partial evidence |  | R1 | Risks & issues | Risk / issue visibility | Are the material delivery risks and issues visible? | Material risks/issues are explicitly listed with impact and current status. | 7.5% | List the current material delivery risks/issues and their delivery impact.
1 | Explicit weakness / material control gap |  | R2 | Risks & issues | Risk response / ownership | Do material risks/issues have accountable responses? | Material risks/issues have an owner, response, target date and escalation path where needed. | 7.5% | Assign accountable owners, response dates and escalation paths to material risks/issues.
0 | Explicit control failure or adverse condition |  | D1 | Decisions & dependencies | Decision / dependency visibility | Are unresolved decisions and critical dependencies visible? | Critical dependencies and unresolved decisions are explicitly identified with delivery impact. | 10% | List unresolved decisions and critical dependencies that can affect delivery.
NE | Not enough evidence to assess |  | D2 | Decisions & dependencies | Decision / dependency control | Are decisions and dependencies actively controlled? | Owners, due dates, aging/impact and escalation are visible for material decisions/dependencies. | 10% | Assign owners/dates and actively track decision/dependency impact and aging.
|  |  | S1 | Scope & requirements | Scope / change clarity | Is the current scope clear and are material changes controlled? | Current scope/baseline is clear; material changes are explicit and incorporated into planning. | 5% | Confirm current scope and ensure material changes are explicitly approved and planned.
|  |  | S2 | Scope & requirements | Acceptance / stakeholder implications | Are acceptance expectations and stakeholder implications clear? | Acceptance criteria, requirement implications and stakeholder alignment are sufficiently explicit. | 5% | Clarify acceptance criteria and any stakeholder/requirement implications affecting delivery.
|  |  | A1 | Ownership & execution | Action ownership / follow-through | Do material delivery actions have owners and due dates? | Consequential actions have accountable owners, dates and visible follow-through. | 7.5% | Assign owners and due dates to material actions; close or replan stale actions.
|  |  | A2 | Ownership & execution | Execution / stakeholder alignment | Are delivery teams and key stakeholders aligned on the current path? | Key handoffs, sequence and stakeholder expectations are aligned enough to execute. | 7.5% | Resolve cross-team/stakeholder alignment gaps and confirm the next handoffs.
|  |  | E1 | Reporting & evidence | Status claims supported by evidence | Are status/RAG/forecast claims supported by dated delivery facts? | Reported status is traceable to current progress, milestones, risks, decisions and other delivery evidence. | 7.5% | Support status/RAG claims with dated delivery facts rather than assertion alone.
|  |  | E2 | Reporting & evidence | Consistency / currentness / decision utility | Is the project information current, internally consistent and useful for decisions? | Key updates are current, contradictions are reconciled or visible, and leadership can act on the information. | 7.5% | Reconcile stale/conflicting updates and make material evidence gaps explicit.